## OVERVIEW
Development Plan
Epic
Product catalog: 1 | Estimated time | Estimated | Min-hours | Max-hours | Min-Points | Max-Points
1 | HIP-40 A first-time visitor can easily find the main navigation menu to navig... WEBSITE DESIGN AND NAVIGATI... | 5 | 10 | 20 | 2.5 | 5
1 | HIP-41 A user can navigate to the Product Catalog to view products. WEBSITE DESIGN AND NAVIGATI.. | 6 | 12 | 24 | 3 | 6
1 | HIP-53 A mobile user wants the website to have a responsive design to easi... WEBSITE DESIGN AND NAVIGATI... | 6 | 12 | 24 | 3 | 6
1 | HIP-21 A user is able to browse the products by color PRODUCT CATALOG | 3 | 6 | 12 | 1.5 | 3
1 | A HIP-45 UI - Seller will be able to manage and delete products posted on the site from an adm... ADMIN PANEL | 6 | 12 | 24 | 3 | 6
Total Hours |  | 104 | 208 | 416
Total Points | 4 hours == 1 point | 26 | 52 | 104 | 13 | 26
Shopping cart / Checkout: 2 |  |  | Min-hours | Max-hours
2 |  |  | 6 | 12 | 1.5 | 3
2 | A HIP-15 A user can change how many units are ordered of an item SHOPPING CART & CHECKOUT |  | 8 | 16 | 2 | 4
2 | HIP-69 A user can add or remove a product to their shopping cart while viewing their cart SHOPPING CART & CHECKOUT |  | 6 | 12 | 1.5 | 3
2 | wHIP-17 A user is able to enter their payment information if it is not saved in the database SHOPPING CART & CHECKOUT |  | 4 | 8 | 1 | 2
2 | HIP-18 A signed in user may choose to save their information or not SHOPPING CART & CHECKOUT |  | 3 | 6 | 0.75 | 1.5
2 | A HIP-19 A signed in user WITH payment info saved with the payment api, then no input of payment info should be neces... |  | 8 | 16 | 2 | 4
2 | SHOPPING CART & CHECKOUT |  | 6 | 12 | 1.5 | 3
2 | HIP-20 A user is able to cancel an order they are currently creating SHOPPING CART & CHECKOUT |  | 4 | 8 | 1 | 2
| HIP-62 Functional Code - A customer is able to enter their shipping information during Registration if they desire SHOPPING CART & CHECKOUT |  | 12 | 24 | 3 | 6
Total Hours |  |  | 57 | 114
Total Points |  |  | 14.25 | 28.5
User Management: 3 |  |  | Min-hours | Max-hours
3
Total Hours |  |  | 0 | 0
Total Points |  |  | 0 | 0
Order management: 4 |  |  | Min-hours | Max-hours
4 | Order tracking |  | 8 | 16 | 2 | 4
| Order history |  | 6 | 12 | 1.5 | 3
| Order status updates |  | 6 | 12 | 1.5 | 3
| Invoicing and receipt generation |  | 6 | 12 | 1.5 | 3
Total Hours |  |  | 26 | 52
Total Points |  |  | 6.5 | 13
Shipping: 5 |  |  | Min-hours | Max-hours
5 | Order tracking |  | 8 | 16 | 2 | 4
| Order history |  | 8 | 12 | 2 | 3
| Order status updates |  | 10 | 12 | 2.5 | 3
| Invoicing and receipt generation |  | 8 | 10 | 2 | 2.5
Total Hours |  |  | 34 | 50
Total Points |  |  | 8.5 | 12.5
User Experience: 6 |  |  | Min-hours | Max-hours
6 | Profile Management |  | 8 | 16 | 2 | 4
| Order history |  | 8 | 12 | 2 | 3
| Order status updates |  | 10 | 12 | 2.5 | 3
| Registration |  | 6 | 10 | 1.5 | 2.5
| Login |  | 4 | 6 | 1 | 1.5
Total Hours |  |  | 36 | 56
Total Points |  |  | 9 | 14
Messaging system: 7 |  |  | Min-hours | Max-hours
7 | Contact form |  | 4 | 8 | 1 | 2
| Contact data management |  | 8 | 12 | 2 | 3
| Promotions email manager |  | 8 | 16 | 2 | 4
Total Hours |  |  | 20 | 36
Total Points |  |  | 5 | 9
Design & Navigation: 8 |  |  | Min-hours | Max-hours
8 | Navbar and links |  | 4 | 8 | 1 | 2
| _Layout - Mobile First |  | 8 | 12 | 2 | 3
| Footer |  | 2 | 4 | 0.5 | 1
| Site.css |  | 4 | 8 | 1 | 2
Total Hours |  |  | 18 | 32
Total Points |  |  | 4.5 | 8
Admin panel: 9 |  |  | Min-hours | Max-hours
9 | User management |  | 10 | 20 | 2.5 | 5
| Product management |  | 10 | 20 | 2.5 | 5
| Order management |  | 12 | 24 | 3 | 6
| Reporting and analytics |  | 3 | 6 | 0.75 | 1.5
Total Hours |  |  | 35 | 70 | 8.75 | 17.5
Total Points |  |  | 8.75 | 17.5 | 2.1875 | 4.375
Project Totals | Number of sprints |  |  |  | Need Average Points / Sprint
Story Points | 5 |  | 108.5 | 206.5 | 63

## SPRINT 1
Sprint
Category Color | User Story |  | Story points
8 | HIP-40 A first-time visitor can easily find the main navigation menu to navigate to the section ... |  | 3
6 | HIP-41 A user can navigate to the Product Catalog to view products. WEBSITE DESIGN AND NAVIGATI... |  | 2
6 | HIP-53 A mobile user wants the website to have a responsive design to easily use on a smart... |  | 2
1 | HIP-21 A user is able to browse the products by color PRODUCT CATALOG |  | 3
1 | HIP-45 UI - Seller will be able to manage and delete products posted on the site from an administrator only scr... ADMIN PANEL |  | 2
9 | HIP-59 Functional Code - Seller will be able to manage and delete products posted on the site from an adminis... |  | 2
3 | HIP-48 UI - A guest will be able to register as a user of the site. USER MANAGEMENT |  | 2
| HIP-13 A user is able to browse through all the available products and color options. PRODUCT CATALOG |  | 3
Target Average | Current sprint
| Hours | Points == Hours / Person
63 | 76 | 19
BurnDown
|  |  |  | Category | Min-points | Max-points | Actual
|  |  |  | Product catalog: 1 |  | 1 | 1
|  |  |  | Shopping cart / Checkout: 2 | 2 | 2 | 2
|  |  |  | User Management: 3 | 3 | 3 | 3
|  |  |  | Order management: 4 | 4 | 4 | 4
|  |  |  | Shipping: 5 | 5 | 5 | 5
|  |  |  | User Experience: 6 | 6 | 6 | 6
|  |  |  | Messaging system: 7 | 7 | 7 | 7
|  |  |  | Navigation: 8 | 8 | 8 | 8
|  |  |  | Admin panel: 9 | 9 | 9 | 9
[5 empty] | 1 | 1 | 1
TOTAL POINTS
|  |  |  | After Sprint | -10 | -10